## Slide 1
Team members: Yakir Helets | Oshri Nuri | Gal Fleissig
Automatic Shift Scheduling
236503 - Project in Software - Android Applications

## Slide 2: Product Backlog

## Slide 3: Introduction

## Slide 4: Sprint 1

## Slide 5: Automatic shift scheduling (algorithm)
The main component which the app is based on.
Given Employees options, the algorithm will produce a valid work schedule, thus saving hassle & precious time for the Employer (instead of usual manual shift management).
Estimated development time: 20 hours
Teammate responsible: Yakir
Risk: Slow performance
Difficulty:

## Slide 6: Time slots configuration (Employer)
The employer has the option of configuring the specific time slots of the shifts for the upcoming week
This can be done only by the employer
Estimated development time: 5 hours
Teammate responsible: Gal
Difficulty:

## Slide 7: Adding scheduling options (Employee)
Every employee has the ability to choose his preferred working hours.
The algorithm will take into consideration everyone’s options.
Estimated development time: 5 hours
Teammate responsible: Oshri
Difficulty:

## Slide 8: View of weekly schedule (User)
After a schedule has been made, every User would be able to view the weekly schedule (of all other members as well).
Estimated development time: 3 hours
Teammate responsible: Oshri
Difficulty:

## Slide 9: Confirm and publish created schedule
After the employees filled out their options of the shifts for the upcoming week and the employer viewed the schedule that was created, the employer can confirm and publish the schedule.
Once the employer does so, the employees will get a notification that the schedule is final
Estimated development time: 7 hours
Teammate responsible: Gal
Difficulty:

## Slide 10: Page of groups that the Employer manages
A convenient display of the groups which managed by the Employer.
Estimated development time: 5 hours
Teammate responsible: Yakir
Difficulty:

## Slide 11: Page of groups that the Employee is a member of
A convenient display of the groups which the Employee is a member of
Estimated development time: 5 hours
Teammate responsible: Yakir
Difficulty:

## Slide 12: Group creation page
The employer can create a new group and invite the employees to be a part of it. The group consists of name, time slots for shifts etc.
Each workplace/division in a workplace can have its own group on Shiftly
Estimated development time: 15 hours
Teammate responsible: Gal
Difficulty:

## Slide 13: Sprint 2

## Slide 14: View employees options (Employer)
Once the employees filled out their options of shifts for the upcoming week, the employer can view those options and give her/his feedback
Estimated development time: 5 hours
Teammate responsible: Gal
Difficulty:

## Slide 15: Manually update an existing schedule (Employer)
Provides the Employer the ability to directly intervene with an existing schedule (i.e: an Employee called in sick).
Estimated development time: 8 hours
Teammate responsible: Yakir
Risk: A manual change might invalidate the correctness of current schedule
Difficulty:

## Slide 16: Daily view of schedule (User)
After a schedule has been made, every User would be able to view the daily schedule (of all other members as well).
Estimated development time: 4 hours
Teammate responsible: Oshri
Difficulty:

## Slide 17: Agenda view of schedule (User)
After a schedule has been made, every User would be able to view his specific weekly schedule.
Estimated development time: 4 hours
Teammate responsible: Oshri
Difficulty:

## Slide 18: Schedule sharing & exporting (User)
After a schedule has been made, every User would have the ability to share it via other apps (i.e “WhatsApp”) or export it to a spreadsheet (i.e “Microsoft Excel”).
Estimated development time: 3 hours
Teammate responsible: Oshri
Difficulty:

## Slide 19: Shift swapping request (Employee)
Provides the Employee the ability to request a shift swapping with another Employee and notifying the Employer.
By approving the request, the previous schedule will be updated accordingly (without reapplying the main algorithm).
Estimated development time: 6 hours
Teammate responsible: Yakir
Risk: Similar to manually update
Difficulty:

## Slide 20: Synchronization with Google calendar
Once all employees filled out their options and the employer confirmed and published the created schedule, both the employees and the employer can export the shift schedule into their own Google calendar accounts
Estimated development time: 6 hours
Teammate responsible: Gal
Difficulty:

## Slide 21: Nice to have

## Slide 22: Hebrew language support
Support for the Hebrew language for Hebrew speakers
Estimated development time: 5 hours
Teammate responsible: Gal
Difficulty:

## Slide 23: SMS integration
Provides an easy and convenient way to be added into an existing group. The Employees will receive a SMS with a link. Upon clicking on it, they will automatically be added to the group.
Framework involved:
Estimated development time: 2 hours
Teammate responsible: Oshri
Difficulty:

## Slide 24: Group message board
Provides the Employer the ability to publish messages to all the other Employees in app.
Estimated development time: 8 hours
Teammate responsible: Yakir
Difficulty: